## Ark1
PROJECT SCHEDULE FOR:
LOFTHUS FRUKT OG SAFT
Project start: 18.11.2019
Project end: 16.12.2019
Workdays total: 21
Red days are holy days.
Key Meetings = Every Monday from 10am to 12pm.
TASK | LEAD ROLE | START | END | DAYS | WEEK 1 ¦ 18.11.2019 | [6 empty] | WEEK 2 ¦ 25.11.2019 | [6 empty] | WEEK 3 ¦ 02.12.2019 | [6 empty] | WEEK 4 ¦ 09.12.2019 | [6 empty] | WEEK 5 ¦ 16.12.2020
PLANNING |  |  |  |  | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M
Key Meetings | Project Manager | Every Monday | Every Monday | 4 | bar: WEEK 1 ¦ 18.11.2019 M; WEEK 2 ¦ 25.11.2019 M; WEEK 3 ¦ 02.12.2019 M; WEEK 4 ¦ 09.12.2019 M; WEEK 5 ¦ 16.12.2020 M
Set up Facebook account | Digital Marketer | 20.11.2019 | 22.11.2019 | 3 | bar: WEEK 1 ¦ 18.11.2019 W to WEEK 1 ¦ 18.11.2019 F
Set up Instagram account | Digital Marketer | 25.11.2019 | 27.11.2019 | 3 | bar: WEEK 2 ¦ 25.11.2019 M to WEEK 2 ¦ 25.11.2019 W
Prepare AD campaigns | Digital Marketer | 02.12.2019 | 05.12.2019 | 4 | bar: WEEK 3 ¦ 02.12.2019 M to WEEK 3 ¦ 02.12.2019 T
Prepare textual content | Copywriter | 19.11.2019 | 22.11.2019 | 4 | bar: WEEK 1 ¦ 18.11.2019 T to WEEK 1 ¦ 18.11.2019 F
DESIGN
Prepare Images | Graphic Designer | 18.11.2019 | 20.11.2019 | 3 | bar: WEEK 1 ¦ 18.11.2019 M to WEEK 1 ¦ 18.11.2019 W
Make Styletile | Graphic Designer | 21.11.2019 | 25.11.2019 | 3 | bar: WEEK 1 ¦ 18.11.2019 T to WEEK 1 ¦ 18.11.2019 F; WEEK 2 ¦ 25.11.2019 M
Make Website Layout | Graphic Designer | 26.11.2019 | 28.11.2019 | 3 | bar: WEEK 2 ¦ 25.11.2019 T to WEEK 2 ¦ 25.11.2019 T
Hand over content to dev | Graphic Designer | 29.11.2019 | 29.11.2019 | 1 | bar: WEEK 2 ¦ 25.11.2019 F
DEVELOP
Set up Homepage | Frontend Developer | 21.11.2019 | 25.11.2019 | 3 | bar: WEEK 1 ¦ 18.11.2019 T to WEEK 1 ¦ 18.11.2019 F; WEEK 2 ¦ 25.11.2019 M
Set up "About" page | Frontend Developer | 25.11.2019 | 26.11.2019 | 2 | bar: WEEK 2 ¦ 25.11.2019 M to WEEK 2 ¦ 25.11.2019 T
Set up "Contact" page | Frontend Developer | 26.11.2019 | 27.11.2019 | 2 | bar: WEEK 2 ¦ 25.11.2019 T to WEEK 2 ¦ 25.11.2019 W
Set up "Products" page | Frontend Developer | 27.11.2019 | 29.11.2019 | 3 | bar: WEEK 2 ¦ 25.11.2019 W to WEEK 2 ¦ 25.11.2019 F
Implement design | Frontend Developer / Graphic Designer | 02.12.2019 | 06.12.2019 | 5 | bar: WEEK 3 ¦ 02.12.2019 M to WEEK 3 ¦ 02.12.2019 F
Make website mobile responsive | Frontend Developer | 05.12.2019 | 06.12.2019 | 2 | bar: WEEK 3 ¦ 02.12.2019 T to WEEK 3 ¦ 02.12.2019 F
Add on-page SEO | Digital Marketer/Frontend Developer | 09.12.2019 | 11.12.2019 | 3 | bar: WEEK 4 ¦ 09.12.2019 M to WEEK 4 ¦ 09.12.2019 W
Website testing | Frontend Developer | 12.11.2019 | 13.11.2019 | 2 | bar: WEEK 4 ¦ 09.12.2019 T to WEEK 4 ¦ 09.12.2019 F
LAUNCH
Launch website | Frontend Developer | 16.11.2019 | 16.11.2019 | 1 | bar: WEEK 5 ¦ 16.12.2020 M
Start and run AD campaigns | Digital Marketer | 16.11.2019 | 16.11.2019 | 1 | bar: WEEK 5 ¦ 16.12.2020 M